## Header
HEADER — Dashboard Title & PM
Field | Value
Dashboard Title | WESTERN & SOUTHERN REGION SDCC PROJECT DASHBOARD ¦ PE-286
Project Code | PE-286
Region | Western & SOUTHERN Region
Project Manager | Hany Kamal

## General_Info
GENERAL INFO — Key Project Dates
Field | Date | Notes
Contract Sign Date | 2024-07-24
Madinah Handover | 2024-08-26
Abha Handover | 2024-10-06
Jizan Handover | 2025-03-02
Jeddah / Makkah HO | 2025-06-22
Contractual TCC | 2026-07-24 | Highlighted orange in dashboard
Expected TCC | 2027-02-17 | Highlighted red in dashboard — delayed

## Commercial_Info
COMMERCIAL INFO (SAR)
Field | Value (SAR) | Tag / Badge | Notes
Org. Contract Value | 388016486
Cont. Adv. Payment | 0
Change Orders | 0
Sub. Cost Claim | 0
Expected Cont. Value | 388016486 |  | Equals Org. Contract Value + Change Orders
Org. Contingency | 34426811
Rem. Contingency | 15596872 | 45.3% | Badge shown in amber/red in dashboard

## Budgetary_Info
BUDGETARY INFO
Field | Value | Tag / Badge | Notes
Rev. Budget Amount | 355587125 |  | SAR
Target POC 2026 | 100% |  | Percentage
Planned POC | 68.8%
Actual POC Till Date | 40.9% |  | Red in dashboard; badge shows gap vs target
Org. Contingency | 34426811 |  | SAR
Rem. Contingency | 15596872 |  | SAR
Contingency Used | 54.7% |  | Amber in dashboard
EOT Status | Submitted |  | Red in dashboard

## Collection_Info
COLLECTION INFO (SAR)
Field | Value (SAR) | Tag % | Color in Dashboard | Notes
Invoiceable Amount | 204059236 | 52.59% | Green
Submitted Invoices | 152961744 | 39.42% | Amber
Approved Invoices | 152961744 | 39.42% | Amber
Collected Adv. | 0 |  | Normal
Col. Amount Inc Adv | 68039022 | 17.54% | Amber
Billing vs Actual POC | 40% / 41% |  | Normal | Text field — shown as-is

## Cash_Flow
CASH FLOW STATUS (SAR Millions)
Field | Value (SAR M) | Bar Width % | Notes
Net Cash Position | -61.2 |  | Shown as hero figure; red background
Hero Sub-label | Outflow exceeds inflow · negative position |  | Descriptive text under the big number
Cash In | 68 | 52.6316 | Green bar; relative to Cash Out (max)
Cash Out | 129.2 | 100% | Orange bar; this is the 100% reference

## Manpower
MANPOWER STATUS
A — Totals
Field | Value | Notes
Total Manpower | 751 | Hero figure — orange background
Direct Labor | 654 | Green segment in donut
Indirect | 97 | Orange segment in donut
Direct Share % | 87.08% | Shown as green text
B — Direct Labor Breakdown
Category | Count | Notes
ALF (Alfanar direct) | 386 | Shown as sub-label under Direct Labor
SC (Subcontractor) | 268 | Shown as sub-label under Direct Labor
C — Donut Chart SVG Parameters (auto-calculated from counts above)
Parameter | Value | Formula / Notes
Direct % of Total | 114.8318 | e.g. 79.6 → used for green arc dasharray
Indirect % of Total | 14.8318 | e.g. 20.4 → used for orange arc dasharray
Green arc dasharray part1 | 114.8318 | stroke-dasharray first value (green)
Green arc dasharray part2 | -14.8318 | stroke-dasharray second value (green)
Orange arc dasharray part1 | 14.8318 | stroke-dasharray first value (orange)
Orange arc dasharray part2 | 85.1682 | stroke-dasharray second value (orange)

## Project_Phases
PROJECT PHASES — Plan vs Actual (%)
Phase | Plan % | Actual % | Delta | Delta Color | Notes
Overall | 92.78 | 84.28 | 8.5 | warn | Red badge
Engineering | 100 | 99.25 | 0.75 | good | Green badge
Equipment | 100 | 95.54 | 4.46 | mild | Amber badge
Construction | 95.92 | 90.82 | 5.1 | warn | Red badge
Installation | 100 | 93.32 | 6.68 | mild | Amber badge
Testing & Commissioning | 68.05 | 22.08 | 45.97 | warn | Red badge; actual bar uses tiny style

## City_Progress
PROGRESS PER CITY — Plan vs Actual (%)
City | Plan % | Actual % | Delta | Delta Color | Notes
Madinah | 92.88 | 83.78 | 9.1 | warn
Abha | 92.15 | 84.33 | 7.82 | mild
Jizan | 90.96 | 81.37 | 9.59 | warn | Trails plan the most
Jeddah | 95.89 | 86.1 | 9.79 | warn
Makkah | 95.71 | 91.03 | 4.68 | mild | Leads on actual completion
Footer Note (italic text shown below chart)

## Timeline
PROJECTS TIMELINE — Monthly Milestones
Month Label | Has Milestone | Milestone Text | Flag Position | Is TCC Cell | TCC Box Label | TCC Box Date | Notes
2024-11-24 | YES | Project Start | above | NO |  |  | First month
2024-12-24 | NO |  |  | NO
2025-01-24 | NO |  |  | NO
2025-02-24 | NO |  |  | NO
2025-03-24 | YES | MADINAH P.C. | above | NO
2025-04-24 | YES | ABHA P.C. | below | NO |  |  | Flag goes below bar
2025-05-24 | NO |  |  | NO
2025-06-24 | YES | JIZAN P.C. | above | NO
2025-07-24 | NO |  |  | NO
2025-08-24 | NO |  |  | NO
2025-09-24 | YES | MAD& ABH Structur Completed | below | NO
2025-10-24 | YES | Jizan Structure Completed | above | NO
2025-11-24 | NO |  |  | NO
2025-12-24 | YES | CET Equip. Delivery | below | NO
2026-01-24 | NO |  |  | NO
2026-02-24 | NO |  |  | NO
2026-03-24 | NO |  |  | NO
2026-04-24 | NO |  |  | NO
2026-05-24 | NO |  |  | NO
2026-06-24 | NO |  |  | YES
2026-07-24 | NO |  |  | YES | Contractual TCC | 24-Jul-26 | Orange cell
2026-08-24 | NO |  |  | NO
2026-09-24 | NO |  |  | NO
2026-10-24 | NO |  |  | NO
2026-11-24 | NO |  |  | NO
2026-12-24 | NO |  |  | NO
2027-01-24 | NO |  |  | NO
2027-02-24 | NO |  |  | YES | Revised TCC | 2027-02-17 | Red cell

## Major_Issues
MAJOR ISSUES STATUS
# | Issue Description | Trade | Entity | Required Action | Priority
1 | Delay Delivery of Low Current 3rd Fix Materials | Procurement | Supplier (Digital Era) | PM to arrange a meeting with supplier top management to enhance the current delivery forecast dates to meet the TCC contractual date. | High
2 | Delay Approval of Jockey Pumps (Fire Pumps Package) | Engineering / Procurement | SE | SE to expedite the approval of Jockey Pumps to start manufacturing of materials and fulfill the supplied flow USA. | High
3 | Delay Approval of LAN/WAN (M6 Routers) Which Fulfill Contract Requirements | Engineering / Procurement | SE | Approved design is to use (M14 routers), delivery duration 20–24 weeks.SE to approve Alfanar proposal to deliver (M6 routers) which have a delivery duration of 6–8 weeks. | High
4 | Delay Delivery of DWDM (PO Issued to AES) – Waiting for Final Confirmation of Recent Traffic Plan | Engineering / Procurement | SE | SE to expedite providing the confirmed recent traffic plan to start manufacturing materials of DWDM. | High

## Equipment_Status
EQUIPMENT STATUS
# | Equipment | Vendor | PO | GAFM | FAT | Delivery | Status
1 | ADMS/DERMS Servers | CET | Issued | 100% | 100% | 100% | OK
2 | CRAC / PACU Units | Zamil | Issued | 100% | 100% | 100% | OK
3 | FM-200 Cylinders | Zamil | Issued | 100% | 100% | 100% | OK
4 | DDC Panels | Marine | Issued | 100% | 100% | 100% | OK
5 | AC/DC Panels | AES | Issued | 100% | 90% | 90% | Delayed
6 | 48 VDC System | AES | Issued | 100% | 0% | 0% | Delayed
7 | Fire Pumps | Zamil | Issued | 80% | 0% | 0% | Delayed
8 | Security System | ITC | Issued | 100% | N/A | 15% | Delayed

## Footer
FOOTER — Classification & Branding
Field | Value
Classification | Public
Prepared Date | 2026-06-03
Department | Control Center
Brand Name | alfanar